## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | User Authentication & Profile Management | 2PD | Vinny
102 | Dashboard Development | 3PD | Vinny
103 | Task Management: Create, Assign, Track Tasks | 4PD | Joel
104 | Basic Notifications | 2PD | Suraj
…
Iteration 2(Medium Priority-updated)
201 | Calendar Integration | 4PD | Joel
202 | Milestone Tracker | 3PD | Suraj
Iteration 3
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
Low Priority (pink)
301 | Basic CRM Integration | 5PD | Joel
302 | Reports Generation | 4PD | Vinny

## Iteration 1 Plan
Iteration Plan 1
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | User Authentication & Profile Management | VR, JD
Planned as part of core functionality (Sprint 1). On track.
102 | Dashboard Development | VR | Planned as part of core functionality (Sprint 1). On track.
103 | Task Management | VR, JD | Planned as part of core functionality (Sprint 1). On track.
104 | Team Management | JD | Planned, but might be slightly delayed due to dependency on task management.
105 | Basic Notifications | VR | Planned, slight delay expected based on other tasks.
106 | Setting Up Development Environment | All Team Members | This is an essential work item. Expected to be completed as per Sprint 1 timeline.
107 | Bug Fixing (Initial Issues) | JD,VR | Planned as ongoing task during Sprint 1. Should be addressed based on priority.
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Web Application | Current concern: Ensuring the smooth integration of the front-end and back-end. Potential concern: Scalability as more features are added. | SV
Database (MySQL or PostgreSQL) | Current concern: Database design for scalability. Potential concern: Data integrity and security. | DP
Cloud Infrastructure (AWS or Azure) | Current concern: Cloud security and resource optimization. Potential concern: Handling traffic spikes. | DP
Version Control (GitHub) | Current concern: Ensuring all team members are committed to following the branching strategy. | VR,SV,DP,JD
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
GitHub | GitHub is used to track code changes and issues. We use GitHub Issues for bug tracking and version control through Git.
Trello | Trello provides an easy-to-use, visual board that helps us track tasks, progress, and deadlines. We can create boards for each sprint, move tasks between columns, and add comments for clarity.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | User Authentication & Profile Management |  | 9PD
102 | Dashboard Development |  | 8PD
103 | Task Management |  | 9PD
104 | Team Management |  | 6PD | 6PD
105 | Basic Notifications |  | 5PD | 5PD
106 | Setting Up Development Environment | 4PD | 4PD
107 | Bug Fixing (Initial Issues) |  | 4PD | 4PD
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | #VALUE! | #VALUE! | #VALUE! | 0 | 0
Total Project Hours |  | 180 hours + 140 hours + 128 hours= 448 hours

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
101 | User Authentication & Profile Management | 3PD | Vinny
102 | Dashboard Development | 4PD | Vinny
103 | Task Management | 5PD | Joel
104 | Task Assignment Notifications | 3PD | Suraj
105 |  | 2PD | Vinny
Create New Task Button (Floating Action Button)
Iteration 2
Iteration 3
Medium Priority
201 | Team Management (Add/remove members, assign roles) | 4PD | Joel
202 | Basic Notifications for Task Assignments & Deadlines | 3PD | Suraj
203 | Task Deadlines Display in Calendar View | 2PD | Vinny
204 | Enhanced Task Detail View (Priority, Due Date) | 3PD | Joel
Low Priority
301 | Basic CRM: Client List Display | 5PD | Vinny
302 | CRM: Client Interaction History and Notes | 4PD | Suraj
303 | Report Generation for Project Progress | 5PD | Vinny
304 | Client Sales Pipeline Visualization | 4PD | Joel

## Iteration 2 Plan
Iteration Plan 2
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
201 | Calendar Integration: Adding functionality to sync the calendar with external tools like Google Calendar or Outlook. | Vinny (Front-End), Joel (Back-End) | Adheres to MVP functionality. Calendar is essential for task management.
202 | Milestone Tracker: Visual milestone tracking for the ongoing projects. | Joel (Back-End), Suraj (Scrum Master) | Key milestone in Sprint 2; tracks project progress.
203 | Basic CRM Integration: Syncing client information with a basic CRM system for managing contacts. | Joel (Back-End) | Planned as part of MVP, ensuring basic client tracking features.
204 | Reports: Basic report generation for project status, task completion, and team performance. | Deep (Product Owner), Joel (Back-End) | Report generation was highlighted for tracking project metrics.
205 | Bug Fixes & Refinements: Addressing bugs from Sprint 1 and improving overall system performance. | All Team Members | Addressing issues from the previous iteration to ensure stability.
206 | Development Environment Setup: Ensure all members have access to the necessary tools, environments, and frameworks. | Suraj (Scrum Master), Deep (Product Owner) | This is a continuation from Sprint 1 to ensure smooth integration.
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Cloud-based Platform (AWS, Firebase, etc.) | Potential issue: Cost, scaling | Joel (Back-End)
ReactJS for Front-End | Concern: Responsiveness, cross-device compatibility | Vinny (Front-End)
Node.js for Back-End | Concern: Database sync issues | Joel (Back-End)
Google Calendar API (for calendar sync) | Potential: Authentication and data syncing challenges | Joel (Back-End)
CRM Integration (e.g., HubSpot API) | Concerns: Data syncing, security | Joel (Back-End)
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Trello | All tasks from Iteration 1 are completed. Iteration 2 is underway.
Google Drive/Docs | Documentation is being updated.No significant changes. All documentation is on track.
Slack | Communication between team members is continuous.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
201 |  | 2PD |  | 5PD
202 |  | 1PD |  | 4PD
203 |  | 1PD |  | 4PD
204 |  | 1PD |  | 3PD
205 |  | 1PD | 2PD
206 | Development Environment Setup: Ensure all members have the necessary tools and environments. | 1PD | 1PD
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | #VALUE! | #VALUE! | #VALUE! | 0 | 0
Total Project Hours |  | 20 hours + 16 hours + 16 hours + 12 hours + 8 hours + 4 hours = 76 hours

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
301 | Final Testing & Bug Fixing | 6PD | Vinny, Joel
302 | Finalizing AI Recommendations | 5PD | Joel, Suraj
303 | Marketing Campaign Features | 4PD | Vinny, Deep
304 | Security Enhancements: Data Encryption | 4PD | Suraj, Deep
Iteration 2
Iteration 3
Medium Priority
305 | AI-powered Reports for Marketing | 3PD | Vinny, Joel
306 | Cloud Infrastructure Improvements | 4PD | Suraj, Joel
Low Priority
307 | Documentation for AI Features | 2PD | Deep, Joel
308 | Multilingual Support Implementation | 4PD | Vinny,Suraj

## Iteration 3 Plan
Iteration Plan 3
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
301 | Final Testing & Bug Fixing: Ensure the platform is bug-free by completing necessary tests. | Vinny, Joel | On track
302 | Finalizing AI Recommendations: Implement AI recommendations for workflow optimization and resource allocation. | Deep, Joel | On track
303 | Security Enhancements: Data Encryption: Implement and finalize data encryption to secure user and client data. | Joel, Vinny | On track
304 | Marketing Campaign Features: Enhance the marketing campaign features, enabling email campaigns and tracking | Vinny, Deep | On track
305 | Multilingual Support Implementation: Add multilingual support for global users to improve accessibility. | Vinny | On track
306 | Documentation for AI Features: Provide comprehensive documentation on the AI features' integration into the platform. | Deep, Joel | On track
307 | Client Reporting Dashboard Enhancements: Enhance the client-facing dashboard for better reporting and analytics. | Vinny, Deep | On track
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Cloud-based infrastructure (AWS) | Scalability, performance issues as user base grows. | Suraj
Frontend: React, Backend: Node.js, Database: PostgreSQL | Integration issues, ensuring API stability. | Suraj
Platform: Web-based, mobile-friendly design. | Cross-browser compatibility and mobile responsiveness. | Suraj
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Trello | Trello is used to manage the backlog, track progress of tasks, and visualize the project’s overall progress. Updates are provided regularly during stand-ups.
Timeline Changes: The timeline has shifted slightly due to minor delays in Iteration 2. Buffer time has been added in Iteration 3 to ensure deliverables are met.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
301 | Final Testing & Bug Fixing | 2PD | 8PD | 4PD | 12PD | Transition
302 | Finalizing AI Recommendations | 2PD | 4PD | 6PD | 10PD | Transition
303 | Security Enhancements: Data Encryption | 2PD | 5PD | 5PD | 10PD | Transition
304 | Marketing Campaign Features | 2PD | 6PD | 6PD | 8PD | Transition
305 | Multilingual Support Implementation | 2PD | 4PD | 4PD | 8PD | Transition
306 | Documentation for AI Features | 1PD | 1PD | 3PD | 5PD | Transition
307 | Client Reporting Dashboard Enhancements | 2PD | 5PD | 7PD | 10PD | Transition
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total Project Hours |  | 136 hours + 140 hours + 252 hours + 52 hours = 580 hours